## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Gather dataset for credit underwriting from Kaggle and validate it | MUST HAVE | Kaggle Account | sakiri mohana murali krishna | 3- Completed
S1 | S1 | US-002 | Perform data preprocessing steps like data cleaning , handle null values etc | MUST HAVE | Google /Jupyter notebook | sakiri mohana murali krishna | 3- Completed
S1 | S1 | US-003 | Conduct initial exploratory data analysis (EDA) to understand trends | SHOULD HAVE | Python Libraries | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-001 | Perform Outlier removal for numerical features, Perform scaling numerical features | MUST HAVE | - | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-002 | Data encoding for categorical features | MUST HAVE | - | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-003 | models (e.g., Logistic Regression, Random Forest) and evaluate performance | MUST HAVE | Scikit-Learn | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-004 | Identify best-performing model based on evaluation metrics | MUST HAVE | - | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-005 | Perform hyperparameter tuning on the best-performing model | MUST HAVE | - | sakiri mohana murali krishna | 3- Completed
S2 | S2 | US-006 | Prepare final model for deployment | MUST HAVE | - | sakiri mohana murali krishna | 3- Completed
S3 | S3 | US-001 | Create a prototype webpage using Streamlit to display insights and predictions | MUST HAVE | Streamlit | sakiri mohana murali krishna | 3- Completed
S4 | S4 | US-001 | Develop a Flask API to serve the model for the Streamlit app or web hosting | MUST HAVE | Flask,PythonAnywhere | sakiri mohana murali krishna | 2- In Progress
Note on F1: Mention the US ID(s) on which the user story depends. -Sumeet Kumar Barua08

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 22.5 | 2 | 5 | 1 | 1.5 | 4 | 1 | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Explore different websites like Kaggle. | 2024-11-08 | 2024-11-09 | - | Data Gathering | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Gather data related to credit analysis underwriting. | 2024-11-11 | 2024-11-11 | - | Data Gathering | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-003 | Provide a brief overview of the dataset. | 2024-11-12 | 2024-11-12 | - | Data Processing | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Handle null values. Perform feature reduction. | 2024-11-13 | 2024-11-13 | - | Data Cleaning | Completed | 1.5 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Conduct basic EDA on relevant features to gain insights. | 2024-11-15 | 2024-11-15 | - | Exploratory Data Analysis | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
SPRINT 2 BACKLOG
US-001 | TASK-001 | Remove outliers manually (e.g., age and income length). | 2024-11-18 | 2024-11-18 | - | Outlier Removal | Completed | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | Fill missing values in numerical features. | 2024-11-19 | 2024-11-19 | - | Imputation | Completed | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-003 | Scale all numerical features. | 2024-11-20 | 2024-11-20 | - | Scaling | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-004 | Encode categorical features. | 2024-11-21 | 2024-11-21 | - | Encoding | Completed | 1.5 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-005 | Train models using classifiers like Logistic Regression, SVC, and Random Forest. | 2024-11-22 | 2024-11-22 | - | Model Training | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-006 | Evaluate the best model. | 2024-11-23 | 2024-11-23 | - | Model Evaluation | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-007 | Perform hyperparameter tuning on the best model. | 2024-11-24 | 2024-11-24 | - | Model Selection | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TASK-008 | Save the final model in a pickle file. | 2024-11-25 | 2024-11-26 | - | Storing model | Completed | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-001 | TASK-001 | Create a Streamlit webpage for the project. | 2024-11-27 | 2024-11-29 | - | Prototype Webpage | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-001 | TASK-001 | Develop a Flask server to handle backend logic. | 2024-12-02 | 2024-12-04 | - | Backend Server | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | TASK-002 | host web server in any webpage hosting platform | 2024-12-05 | 2024-12-06 | - | Hosting | In Process | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on E2: 9/15/2016 or 15-Sep-2016 -Please enter the dates in either of these formats
Note on I3: This is the total task estimated in hours for all the user stories -Sumeet Kumar Barua08
Note on J3: Pending effort hours after completion of day 1 work -Sumeet Kumar Barua08
Note on K3: Pending effort hours after completion of day 2 work -Sumeet Kumar Barua08
Note on L3: Pending effort hours after completion of day 3 work -Sumeet Kumar Barua08
Note on M3: Pending effort hours after completion of day 4 work -Sumeet Kumar Barua08
Note on N3: Pending effort hours after completion of day 5 work -Sumeet Kumar Barua08
Note on O3: Pending effort hours after completion of day 6 work -Sumeet Kumar Barua08
Note on P3: Pending effort hours after completion of day 7 work -Sumeet Kumar Barua08
Note on Q3: Pending effort hours after completion of day 8 work -Sumeet Kumar Barua08
Note on R3: Pending effort hours after completion of day 9 work -Sumeet Kumar Barua08
Note on S3: Pending effort hours after completion of day 10 work -Sumeet Kumar Barua08
Note on T3: Pending effort hours after completion of day 11 work -Sumeet Kumar Barua08
Note on U3: Pending effort hours after completion of day 12 work -Sumeet Kumar Barua08
Note on V3: Pending effort hours after completion of day 13 work -Sumeet Kumar Barua08
Note on W3: Pending effort hours after completion of day 14 work -Sumeet Kumar Barua08

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2024-11-04 | 2024-11-17 | Aayushi Pandey | Exploring Drive links for self study | Time waste in documentation | Regular coding | Focused on Organization
2 | S2 | 2024-11-18 | 2024-11-25 | Aayushi Pandey | Implementing advanced preprocessing | Skipping daily coding task | Experimenting | Enhanced preprocessing techniques
3 | S3 | 2024-11-25 | 2024-11-28 | Aayushi Pandey | Regularly commit git Changes | Procastinating | Maintaining Workflow | Improved version control
4 | S4 | 2024-12-01 | 2024-12-08 | Aayushi Pandey | Exploring cloud platforms |  |  | Gained familiarity with tools
5
6
7

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Lack of clarity in Project | Conducted a detailed discussion with mentor
S2 | Day 12 | Difficulty in understanding Preprocessing steps | A detailed explanation given by mentor
S3 | Day 20 | Difficulty in implementing virtual environment | Explained by the mentor by screen sharing
S4 | Day 23 | Difficulty in filling Agile documentation | Dedicated meeting for Agile Documenation